## Sheds
id	job_id	precedence	display_text	free_text	owned_by	change_log	sort_order	SQL	SQL2	newSort
70	9	pretask	Quote sent date		1		1	5	5.01	1.01
71	9	pretask	3 day follow up – received quote check		1		2	5	5.02	1.02
72	9	pretask	Site visit requested		1		3	5	5.03	1.03
73	9	pretask	14 days later follow up		1		4	5	5.04	1.04
74	9	pretask	21 days later follow up		1		5	5	5.05	1.05
75	9	pretask	Monthly thereafter follow up (1)		1		6	5	5.06	1.06
76	9	pretask	Monthly thereafter follow up (2)		1		6	5	5.06	1.07
77	9	pretask	Final Monthly follow up		1		6	5	5.06	1.08
78	10	pretask	Set follow up date		1		1	6	6.01	2.09
79	10	pretask	Set follow up schedule		1		2	6	6.02	2.1
80	11	pretask	Site inspection		1		1	7	7.01	3.11
81	11	pretask	Requotes		1		2	7	7.02	3.12
82	12	pretask	Deposit date		1		10	8	8.10	4.13
83	12	pretask	Distribute information		1		20	8	8.20	4.14
84	12	pretask	Building permit admin		1		30	8	8.30	4.15
85	12	pretask	Builder	Date:	1		40	8	8.40	4.16
86	14	pretask	Customer quote review / provided		1		10	10	10.10	5.17
87	14	pretask	Customer quote sent		1		20	10	10.20	5.18
88	14	pretask	Customer acceptance prepped		1		30	10	10.30	5.19
89	14	pretask	Customer signed acceptance	Date:	1		40	10	10.40	5.2
90	14	pretask	Customer invoiced PP and BP dep	Date:	1		50	10	10.50	5.21
91	14	pretask	Payment received	Date:	1		60	10	10.60	5.22
118	20	pretask	Title / POS		1		12	10.5	10.5.12	6.23
119	20	pretask	Covenants		1		13	10.5	10.5.13	6.24
120	20	pretask	BAL rating / BMO		1		14	10.5	10.5.14	6.25
121	20	pretask	Planning permit if required		1		15	10.5	10.5.15	6.26
122	20	pretask	Proposed site plan		1		16	10.5	10.5.16	6.27
123	20	pretask	Sewer plan		1		17	10.5	10.5.17	6.28
124	20	pretask	LPOD		1		18	10.5	10.5.18	6.29
125	20	pretask	RBP selected		1		19	10.5	10.5.19	6.3
126	20	pretask	Kit quote		1		110	10.5	10.5.110	6.31
127	20	pretask	Construction quote		1		111	10.5	10.5.111	6.32
128	20	pretask	Draft Site plan sent to design		1		112	10.5	10.5.112	6.33
129	20	pretask	Site plan returned from design		1		113	10.5	10.5.113	6.33999999999999
130	20	pretask	Engineering		16		114	10.5	10.5.114	6.34999999999999
92	15	pretask	Design Site plan		1		1	11	11.01	7.35999999999999
93	15	pretask	Planning permit application submitted	Date:	1		1	11	11.01	7.36999999999999
94	15	pretask	Planning permit fee paid	Date:	1		2	11	11.02	7.37999999999999
95	15	pretask	Planning permit contact	Name:	1		3	11	11.03	7.38999999999999
96	15	pretask	Follow up schedule		1		7	11	11.07	7.39999999999999
97	15	pretask	Planning permit issued	Date:	1		9	11	11.09	7.40999999999999
98	16	pretask	Design Site plan		1		1	12	12.01	8.41999999999999
99	16	pretask	Signed Building Surveyor appointed		1		2	12	12.02	8.42999999999999
100	16	pretask	Building Permit application submitted date		1		3	12	12.03	8.43999999999999
101	16	pretask	RFI received		1		4	12	12.04	8.44999999999999
105	16	pretask	RFI responded		1		6	12	12.06	8.45999999999999
106	16	pretask	Building Surveyor Invoice received		1		7	12	12.07	8.46999999999999
107	16	pretask	Balance of BP to be invoiced or not required	2 tick options not yet included: Yes or No	1		8	12	12.08	8.47999999999999
108	16	pretask	Building Surveyor Invoice paid	Date:	1		9	12	12.09	8.48999999999999
109	16	pretask	Permit issued date	Date:	1		10	12	12.10	8.49999999999999
110	16	pretask	Permit Number	Enter permit number:	1		11	12	12.11	8.50999999999999
102	16	pretask	RFI action required 1		1		05a	12	12.05a	8.51999999999999
103	16	pretask	RFI action required 2		1		05b	12	12.05b	8.52999999999999
104	16	pretask	RFI action required 3		1		05c	12	12.05c	8.53999999999999
111	17	pretask	Set follow up schedules weekly, fortnightly, monthly		1		1	13	13.01	9.54999999999999
114	17	pretask	Permit issued	Date:	1		1	13	13.01	9.55999999999999
112	17	pretask	Sent Engineering	Date:	1		2	13	13.02	9.56999999999999
115	17	pretask	Permit Number	Enter permit number:	1		2	13	13.02	9.57999999999999
113	17	pretask	Sent Elevations	Date:	1		3	13	13.03	9.58999999999999
116	18	pretask	Confirm kit ordered		1		1	14	14.01	10.6
117	19	pretask	Delivery date set		1		2	15	15.02	11.61
33	1	pretask	Check site issues		1		1.1	16	16.01	12.62
34	1	pretask	Confirm siting		1		1.2	16	16.01	12.63
224	44		Contract Preparation		1		1	16.5	16.5.01	13.64
225	44		Building construction contract signed		1		2	16.5	16.5.02	13.65
35	2	pretask	Select contractor	Enter name here:	1		2.1	17	17.02	14.66
36	2	pretask	Issue purchase order		1		2.2	17	17.02	14.67
37	2	pretask	Call up concretor		1		2.3	17	17.02	14.68
38	2	pretask	Set start date		1		2.4	17	17.02	14.69
39	2	pretask	Planned pour date	Planned date:	1		2.45	17	17.02	14.7
40	2	pretask	Contact home owner to advise commencement		1		2.5	17	17.03	14.71
41	2	pretask	Start confirmed with contractor		1		2.6	17	17.03	14.72
42	2	pretask	Measure set out and slab		1		2.7	17	17.03	14.73
43	2	pretask	Concrete poured		1		2.8	17	17.03	14.74
44	2	postask	Advise accounts to invoice		1		2.9	17	17.03	14.75
45	3	pretask	Select contractor	Contractor name:	1		3.1	18	18.03	15.76
46	3	pretask	Confirm delivery date	Delivery date:	1		3.15	18	18.03	15.77
47	3	pretask	Issue purchase order		1		3.2	18	18.03	15.78
48	3	pretask	Call up erector - slab pour day		1		3.3	18	18.03	15.79
49	3	pretask	Set start date - 7 days after slab pour		1		3.4	18	18.03	15.8
50	3	pretask	Contact home owner to advise erecting commencement date		1		3.5	18	18.04	15.81
51	3	pretask	Start confirmed with erector		1		3.6	18	18.04	15.82
52	3	pretask	Confirm frame erected		1		3.7	18	18.04	15.83
53	3	pretask	Check frame		1		3.75	18	18.04	15.84
54	3	postask	Advise accounts to Invoice frame		1		3.8	18	18.04	15.85
55	3	pretask	Confirm cladding complete		1		3.85	18	18.04	15.86
56	3	pretask	Check cladding		1		3.9	18	18.04	15.87
57	3	postask	Advise accounts to invoice		1		3.95	18	18.04	15.88
58	4	pretask	Establish stormwater connection point		1		4.1	19	19.04	16.89
59	4	pretask	Select plumber		1		4.2	19	19.04	16.9
60	4	pretask	Book trencher		1		4.3	19	19.04	16.91
61	4	pretask	Issue Purchase order for plumber		1		4.4	19	19.04	16.92
62	4	pretask	Confirm trenching day set	Date:	1		4.5	19	19.05	16.93
63	4	pretask	Confirm plumber booked to start	Date:	1		4.6	19	19.05	16.94
64	4	pretask	Confirm trenching done		1		4.65	19	19.05	16.95
65	4	pretask	Confirm plumber start	Date:	1		4.7	19	19.05	16.96
66	4	pretask	Confirm stormwater installed		1		4.75	19	19.05	16.97
67	4	postask	Book final inspection by building surveyor		1		4.8	19	19.05	16.98
68	4	postask	Confirm final certificate is issued		1		4.85	19	19.05	16.99
69	4	postask	Advise accounts to invoice		1		4.9	19	19.05	17

id	user_id	role_id	product_id	display_text	free_text	antecedent_array	decendant_array	reminder_id	change_log	sort_order	tier	SQL
1001			3	Quotes			1002	1		1	500
1002			3	Feeling good quotes		1001	1003	1		3	500
1003			3	Pre Deposit		1002	1004	1		5	500
1004			3	Deposit		1003	1005	1		7	500
1005			3	Pre-Permit		1004	1006	1		9	500
1006			3	Document Preparation		1005	1007	1		11	500
1007			3	Planning Permit		1006	1008	1		13	500
1008			3	Building Permit		1007	1009	1		15	500
1009			3	Owner doing own Permit		1008	1010	1		17	500
1010			3	Kit ordered into Production		1009	1011	1		19	500
1011			3	Kit Delivery date set		1010	1012	1		21	500
1012			3	Site Appraisal		1011	1013	1		23	500
1013	12		3	Contract Preparation		1012	1014	1		25	500
1014	12		3	Concreting		1013	1015	1		27	500
1015	12		3	Erecting		1014	1016	1		29	500
1016	12		3	Plumbing		1015		1		31	500

id	user_id	role_id	product_id	display_text	free_text	antecedent_array	decendant_array	reminder_id	change_log	sort_order	tier	id	sort_order
9	1	1	1	Quotes			10	1		5	500	9	5
10	1	1	1	Feeling good quotes		9	11	1		6	500	10	6
11	1	1	1	Pre Deposit		10	12	1		7	500	11	7
12	1	1	1	Deposit		11	14	1		8	500	12	8
14	1	1	1	Pre-Permit		12	20	1		10	500	14	10
20	1	1	1	Document Preparation		14	15	1		10.5	500	20	10.5
15	1	1	1	Planning Permit		20	16	1		11	500	15	11
16	1	1	1	Building Permit		15	17	1		12	500	16	12
17	1	1	1	Owner doing own Permit		16	18	1		13	500	17	13
18	1	1	1	Kit ordered into Production		17	19	1		14	500	18	14
19	1	1	1	Kit Delivery date set		18	1	1		15	500	19	15
1	1	1	1	Site Appraisal		19	48			16	500	1	16
44	1		1	Contract Preparation		1	2			16.5	500	44	16.5
2	1	1	1	Concreting		44	3	1		17	500	2	17
3	1	1	1	Erecting		2	4	1		18	500	3	18
4	1	1	1	Plumbing		3		1		19	500	4	19

id	user_id	role_id	product_id	display_text	free_text	antecedent_array	decendant_array	reminder_id	change_log	sort_order	tier	xx	x	newSort	SQL	ID
id	owned_by			display_text	free_text	antecedent_array	decendant_array		change_log	sort_order	tier	SQL	SQL2	newSort	SQL	ID
9	1	1	4	Quotes		null	389	1		5	500			1	INSERT INTO public.job_templates(id, product_id, display_text, antecedent_array, decendant_array, sort_order, tier) VALUES (380, 3, 'Quotes', ?, ?, ?);	380	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('1.00', '500', 4, 1, null, 389, 380, 1, 'Quotes');
70	1	9	4	Quote sent date		380	382	1		1	501	5	5.01	1.01		381	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('1.01', '501', 4, 1, 380, 382, 381, 1, 'Quote sent date');
71	1	9	4	3 day follow up – received quote check		381	383	1		2	501	5	5.02	1.02		382	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('1.02', '501', 4, 1, 381, 383, 382, 1, '3 day follow up – received quote check');
72	1	9	4	Site visit requested		382	384	1		3	501	5	5.03	1.03		383	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('1.03', '501', 4, 1, 382, 384, 383, 1, 'Site visit requested');
73	1	9	4	14 days later follow up		383	385	1		4	501	5	5.04	1.04		384	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('1.04', '501', 4, 1, 383, 385, 384, 1, '14 days later follow up');
74	1	9	4	21 days later follow up		384	386	1		5	501	5	5.05	1.05		385	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('1.05', '501', 4, 1, 384, 386, 385, 1, '21 days later follow up');
75	1	9	4	Monthly thereafter follow up (1)		385	387	1		6	501	5	5.06	1.06		386	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('1.06', '501', 4, 1, 385, 387, 386, 1, 'Monthly thereafter follow up (1)');
76	1	9	4	Monthly thereafter follow up (2)		386	388	1		6	501	5	5.06	1.07		387	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('1.07', '501', 4, 1, 386, 388, 387, 1, 'Monthly thereafter follow up (2)');
77	1	9	4	Final Monthly follow up		387	390	1		6	501	5	5.06	1.08		388	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('1.08', '501', 4, 1, 387, 390, 388, 1, 'Final Monthly follow up');
10	12	1	4	Feeling good quotes		380	392	1		6	500			2		389	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('2.00', '500', 4, 1, 380, 392, 389, 12, 'Feeling good quotes');
78	12	10	4	Set follow up date		389	391	1		1	501	6	6.01	2.09		390	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('2.09', '501', 4, 1, 389, 391, 390, 12, 'Set follow up date');
79	12	10	4	Set follow up schedule		390	393	1		2	501	6	6.02	2.1		391	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('2.10', '501', 4, 1, 390, 393, 391, 12, 'Set follow up schedule');
11	12	1	4	Pre Deposit		389	395	1		7	500			3		392	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('3.00', '500', 4, 1, 389, 395, 392, 12, 'Pre Deposit');
80	12	11	4	Site inspection		392	394	1		1	501	7	7.01	3.11		393	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('3.11', '501', 4, 1, 392, 394, 393, 12, 'Site inspection');
81	12	11	4	Requotes		393	396	1		2	501	7	7.02	3.12		394	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('3.12', '501', 4, 1, 393, 396, 394, 12, 'Requotes');
12	12	1	4	Deposit		392	400	1		8	500			4		395	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('4.00', '500', 4, 1, 392, 400, 395, 12, 'Deposit');
82	12	12	4	Deposit date		395	397	1		10	501	8	8.10	4.13		396	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('4.13', '501', 4, 1, 395, 397, 396, 12, 'Deposit date');
83	12	12	4	Distribute information		396	398	1		20	501	8	8.20	4.14		397	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('4.14', '501', 4, 1, 396, 398, 397, 12, 'Distribute information');
84	12	12	4	Building permit admin		397	399	1		30	501	8	8.30	4.15		398	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('4.15', '501', 4, 1, 397, 399, 398, 12, 'Building permit admin');
85	12	12	4	Builder	Date:	398	401	1		40	501	8	8.40	4.16		399	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('4.16', '501', 4, 1, 398, 401, 399, 12, 'Builder');
14	12	1	4	Pre-Permit		395	407	1		10	500			5		400	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('5.00', '500', 4, 1, 395, 407, 400, 12, 'Pre-Permit');
86	12	14	4	Customer quote review / provided		400	402	1		10	501	10	10.10	5.17		401	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('5.17', '501', 4, 1, 400, 402, 401, 12, 'Customer quote review / provided');
87	12	14	4	Customer quote sent		401	403	1		20	501	10	10.20	5.18		402	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('5.18', '501', 4, 1, 401, 403, 402, 12, 'Customer quote sent');
88	12	14	4	Customer acceptance prepped		402	404	1		30	501	10	10.30	5.19		403	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('5.19', '501', 4, 1, 402, 404, 403, 12, 'Customer acceptance prepped');
89	12	14	4	Customer signed acceptance	Date:	403	405	1		40	501	10	10.40	5.2		404	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('5.20', '501', 4, 1, 403, 405, 404, 12, 'Customer signed acceptance');
90	12	14	4	Customer invoiced PP and BP dep	Date:	404	406	1		50	501	10	10.50	5.21		405	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('5.21', '501', 4, 1, 404, 406, 405, 12, 'Customer invoiced PP and BP dep');
91	12	14	4	Payment received	Date:	405	408	1		60	501	10	10.60	5.22		406	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('5.22', '501', 4, 1, 405, 408, 406, 12, 'Payment received');
20	13	1	4	Document Preparation		400	421	1		10.5	500			6		407	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('6.00', '500', 4, 1, 400, 421, 407, 13, 'Document Preparation');
118	13	20	4	Title / POS		407	409	1		12	501	10.5	10.5.12	6.23		408	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('6.23', '501', 4, 1, 407, 409, 408, 13, 'Title / POS');
119	13	20	4	Covenants		408	410	1		13	501	10.5	10.5.13	6.24		409	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('6.24', '501', 4, 1, 408, 410, 409, 13, 'Covenants');
120	13	20	4	BAL rating / BMO		409	411	1		14	501	10.5	10.5.14	6.25		410	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('6.25', '501', 4, 1, 409, 411, 410, 13, 'BAL rating / BMO');
121	13	20	4	Planning permit if required		410	412	1		15	501	10.5	10.5.15	6.26		411	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('6.26', '501', 4, 1, 410, 412, 411, 13, 'Planning permit if required');
122	13	20	4	Proposed site plan		411	413	1		16	501	10.5	10.5.16	6.27		412	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('6.27', '501', 4, 1, 411, 413, 412, 13, 'Proposed site plan');
123	13	20	4	Sewer plan		412	414	1		17	501	10.5	10.5.17	6.28		413	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('6.28', '501', 4, 1, 412, 414, 413, 13, 'Sewer plan');
124	13	20	4	LPOD		413	415	1		18	501	10.5	10.5.18	6.29		414	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('6.29', '501', 4, 1, 413, 415, 414, 13, 'LPOD');
125	13	20	4	RBP selected		414	416	1		19	501	10.5	10.5.19	6.3		415	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('6.30', '501', 4, 1, 414, 416, 415, 13, 'RBP selected');
126	13	20	4	Kit quote		415	417	1		110	501	10.5	10.5.110	6.31		416	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('6.31', '501', 4, 1, 415, 417, 416, 13, 'Kit quote');
127	13	20	4	Construction quote		416	418	1		111	501	10.5	10.5.111	6.32		417	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('6.32', '501', 4, 1, 416, 418, 417, 13, 'Construction quote');
128	13	20	4	Draft Site plan sent to design		417	419	1		112	501	10.5	10.5.112	6.33		418	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('6.33', '501', 4, 1, 417, 419, 418, 13, 'Draft Site plan sent to design');
129	13	20	4	Site plan returned from design		418	420	1		113	501	10.5	10.5.113	6.33999999999999		419	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('6.34', '501', 4, 1, 418, 420, 419, 13, 'Site plan returned from design');
130	13	20	4	Engineering		419	422	1		114	501	10.5	10.5.114	6.34999999999999		420	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('6.35', '501', 4, 1, 419, 422, 420, 13, 'Engineering');
15	13	1	4	Planning Permit		407	428	1		11	500			7		421	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('7.00', '500', 4, 1, 407, 428, 421, 13, 'Planning Permit');
92	13	15	4	Design Site plan		421	423	1		1	501	11	11.01	7.35999999999999		422	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('7.36', '501', 4, 1, 421, 423, 422, 13, 'Design Site plan');
93	13	15	4	Planning permit application submitted	Date:	422	424	1		1	501	11	11.01	7.36999999999999		423	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('7.37', '501', 4, 1, 422, 424, 423, 13, 'Planning permit application submitted');
94	13	15	4	Planning permit fee paid	Date:	423	425	1		2	501	11	11.02	7.37999999999999		424	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('7.38', '501', 4, 1, 423, 425, 424, 13, 'Planning permit fee paid');
95	13	15	4	Planning permit contact	Name:	424	426	1		3	501	11	11.03	7.38999999999999		425	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('7.39', '501', 4, 1, 424, 426, 425, 13, 'Planning permit contact');
96	13	15	4	Follow up schedule		425	427	1		7	501	11	11.07	7.39999999999999		426	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('7.40', '501', 4, 1, 425, 427, 426, 13, 'Follow up schedule');
97	13	15	4	Planning permit issued	Date:	426	429	1		9	501	11	11.09	7.40999999999999		427	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('7.41', '501', 4, 1, 426, 429, 427, 13, 'Planning permit issued');
16	13	1	4	Building Permit		421	442	1		12	500			8		428	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('8.00', '500', 4, 1, 421, 442, 428, 13, 'Building Permit');
98	13	16	4	Design Site plan		428	430	1		1	501	12	12.01	8.41999999999999		429	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('8.42', '501', 4, 1, 428, 430, 429, 13, 'Design Site plan');
99	13	16	4	Signed Building Surveyor appointed		429	431	1		2	501	12	12.02	8.42999999999999		430	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('8.43', '501', 4, 1, 429, 431, 430, 13, 'Signed Building Surveyor appointed');
100	13	16	4	Building Permit application submitted date		430	432	1		3	501	12	12.03	8.43999999999999		431	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('8.44', '501', 4, 1, 430, 432, 431, 13, 'Building Permit application submitted date');
101	13	16	4	RFI received		431	433	1		4	501	12	12.04	8.44999999999999		432	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('8.45', '501', 4, 1, 431, 433, 432, 13, 'RFI received');
105	13	16	4	RFI responded		432	434	1		6	501	12	12.06	8.45999999999999		433	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('8.46', '501', 4, 1, 432, 434, 433, 13, 'RFI responded');
106	13	16	4	Building Surveyor Invoice received		433	435	1		7	501	12	12.07	8.46999999999999		434	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('8.47', '501', 4, 1, 433, 435, 434, 13, 'Building Surveyor Invoice received');
107	13	16	4	Balance of BP to be invoiced or not required	2 tick options not yet included: Yes or No	434	436	1		8	501	12	12.08	8.47999999999999		435	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('8.48', '501', 4, 1, 434, 436, 435, 13, 'Balance of BP to be invoiced or not required');
108	13	16	4	Building Surveyor Invoice paid	Date:	435	437	1		9	501	12	12.09	8.48999999999999		436	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('8.49', '501', 4, 1, 435, 437, 436, 13, 'Building Surveyor Invoice paid');
109	13	16	4	Permit issued date	Date:	436	438	1		10	501	12	12.10	8.49999999999999		437	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('8.50', '501', 4, 1, 436, 438, 437, 13, 'Permit issued date');
110	13	16	4	Permit Number	Enter permit number:	437	439	1		11	501	12	12.11	8.50999999999999		438	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('8.51', '501', 4, 1, 437, 439, 438, 13, 'Permit Number');
102	13	16	4	RFI action required 1		438	440	1		05a	501	12	12.05a	8.51999999999999		439	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('8.52', '501', 4, 1, 438, 440, 439, 13, 'RFI action required 1');
103	13	16	4	RFI action required 2		439	441	1		05b	501	12	12.05b	8.52999999999999		440	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('8.53', '501', 4, 1, 439, 441, 440, 13, 'RFI action required 2');
104	13	16	4	RFI action required 3		440	443	1		05c	501	12	12.05c	8.53999999999999		441	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('8.54', '501', 4, 1, 440, 443, 441, 13, 'RFI action required 3');
17	12	1	4	Owner doing own Permit		428	448	1		13	500			9		442	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('9.00', '500', 4, 1, 428, 448, 442, 12, 'Owner doing own Permit');
111	12	17	4	Set follow up schedules weekly, fortnightly, monthly		442	444	1		1	501	13	13.01	9.54999999999999		443	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('9.55', '501', 4, 1, 442, 444, 443, 12, 'Set follow up schedules weekly, fortnightly, monthly');
114	12	17	4	Permit issued	Date:	443	445	1		1	501	13	13.01	9.55999999999999		444	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('9.56', '501', 4, 1, 443, 445, 444, 12, 'Permit issued');
112	12	17	4	Sent Engineering	Date:	444	446	1		2	501	13	13.02	9.56999999999999		445	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('9.57', '501', 4, 1, 444, 446, 445, 12, 'Sent Engineering');
115	12	17	4	Permit Number	Enter permit number:	445	447	1		2	501	13	13.02	9.57999999999999		446	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('9.58', '501', 4, 1, 445, 447, 446, 12, 'Permit Number');
113	12	17	4	Sent Elevations	Date:	446	449	1		3	501	13	13.03	9.58999999999999		447	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('9.59', '501', 4, 1, 446, 449, 447, 12, 'Sent Elevations');
18	12	1	4	Kit ordered into Production		442	450	1		14	500			10		448	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('10.00', '500', 4, 1, 442, 450, 448, 12, 'Kit ordered into Production');
116	12	18	4	Confirm kit ordered		448	451	1		1	501	14	14.01	10.6		449	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('10.60', '501', 4, 1, 448, 451, 449, 12, 'Confirm kit ordered');
19	12	1	4	Kit Delivery date set		448	452	1		15	500			11		450	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('11.00', '500', 4, 1, 448, 452, 450, 12, 'Kit Delivery date set');
117	12	19	4	Delivery date set		450	453	1		2	501	15	15.02	11.61		451	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('11.61', '501', 4, 1, 450, 453, 451, 12, 'Delivery date set');
1	12	1	4	Site Appraisal		450	455	1		16	500			12		452	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('12.00', '500', 4, 1, 450, 455, 452, 12, 'Site Appraisal');
33	12	1	4	Check site issues		452	454	1		1.1	501	16	16.01	12.62		453	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('12.62', '501', 4, 1, 452, 454, 453, 12, 'Check site issues');
34	12	1	4	Confirm siting		453	456	1		1.2	501	16	16.01	12.63		454	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('12.63', '501', 4, 1, 453, 456, 454, 12, 'Confirm siting');
44	12		4	Contract Preparation		452	458	1		16.5	500			13		455	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('13.00', '500', 4, 1, 452, 458, 455, 12, 'Contract Preparation');
224	12	44	4	Contract Preparation		455	457	1		1	501	16.5	16.5.01	13.64		456	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('13.64', '501', 4, 1, 455, 457, 456, 12, 'Contract Preparation');
225	12	44	4	Building construction contract signed		456	459	1		2	501	16.5	16.5.02	13.65		457	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('13.65', '501', 4, 1, 456, 459, 457, 12, 'Building construction contract signed');
2	12	1	4	Concreting		455	469	1		17	500			14		458	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('14.00', '500', 4, 1, 455, 469, 458, 12, 'Concreting');
35	12	2	4	Select contractor	Enter name here:	458	460	1		2.1	501	17	17.02	14.66		459	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('14.66', '501', 4, 1, 458, 460, 459, 12, 'Select contractor');
36	12	2	4	Issue purchase order		459	461	1		2.2	501	17	17.02	14.67		460	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('14.67', '501', 4, 1, 459, 461, 460, 12, 'Issue purchase order');
37	12	2	4	Call up concretor		460	462	1		2.3	501	17	17.02	14.68		461	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('14.68', '501', 4, 1, 460, 462, 461, 12, 'Call up concretor');
38	12	2	4	Set start date		461	463	1		2.4	501	17	17.02	14.69		462	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('14.69', '501', 4, 1, 461, 463, 462, 12, 'Set start date');
39	12	2	4	Planned pour date	Planned date:	462	464	1		2.45	501	17	17.02	14.7		463	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('14.70', '501', 4, 1, 462, 464, 463, 12, 'Planned pour date');
40	12	2	4	Contact home owner to advise commencement		463	465	1		2.5	501	17	17.03	14.71		464	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('14.71', '501', 4, 1, 463, 465, 464, 12, 'Contact home owner to advise commencement');
41	12	2	4	Start confirmed with contractor		464	466	1		2.6	501	17	17.03	14.72		465	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('14.72', '501', 4, 1, 464, 466, 465, 12, 'Start confirmed with contractor');
42	12	2	4	Measure set out and slab		465	467	1		2.7	501	17	17.03	14.73		466	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('14.73', '501', 4, 1, 465, 467, 466, 12, 'Measure set out and slab');
43	12	2	4	Concrete poured		466	468	1		2.8	501	17	17.03	14.74		467	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('14.74', '501', 4, 1, 466, 468, 467, 12, 'Concrete poured');
44	12	2	4	Advise accounts to invoice		467	470	1		2.9	501	17	17.03	14.75		468	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('14.75', '501', 4, 1, 467, 470, 468, 12, 'Advise accounts to invoice');
3	12	1	4	Erecting		458	483	1		18	500			15		469	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('15.00', '500', 4, 1, 458, 483, 469, 12, 'Erecting');
45	12	3	4	Select contractor	Contractor name:	469	471	1		3.1	501	18	18.03	15.76		470	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('15.76', '501', 4, 1, 469, 471, 470, 12, 'Select contractor');
46	12	3	4	Confirm delivery date	Delivery date:	470	472	1		3.15	501	18	18.03	15.77		471	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('15.77', '501', 4, 1, 470, 472, 471, 12, 'Confirm delivery date');
47	12	3	4	Issue purchase order		471	473	1		3.2	501	18	18.03	15.78		472	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('15.78', '501', 4, 1, 471, 473, 472, 12, 'Issue purchase order');
48	12	3	4	Call up erector - slab pour day		472	474	1		3.3	501	18	18.03	15.79		473	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('15.79', '501', 4, 1, 472, 474, 473, 12, 'Call up erector - slab pour day');
49	12	3	4	Set start date - 7 days after slab pour		473	475	1		3.4	501	18	18.03	15.8		474	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('15.80', '501', 4, 1, 473, 475, 474, 12, 'Set start date - 7 days after slab pour');
50	12	3	4	Contact home owner to advise erecting commencement date		474	476	1		3.5	501	18	18.04	15.81		475	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('15.81', '501', 4, 1, 474, 476, 475, 12, 'Contact home owner to advise erecting commencement date');
51	12	3	4	Start confirmed with erector		475	477	1		3.6	501	18	18.04	15.82		476	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('15.82', '501', 4, 1, 475, 477, 476, 12, 'Start confirmed with erector');
52	12	3	4	Confirm frame erected		476	478	1		3.7	501	18	18.04	15.83		477	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('15.83', '501', 4, 1, 476, 478, 477, 12, 'Confirm frame erected');
53	12	3	4	Check frame		477	479	1		3.75	501	18	18.04	15.84		478	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('15.84', '501', 4, 1, 477, 479, 478, 12, 'Check frame');
54	12	3	4	Advise accounts to Invoice frame		478	480	1		3.8	501	18	18.04	15.85		479	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('15.85', '501', 4, 1, 478, 480, 479, 12, 'Advise accounts to Invoice frame');
55	12	3	4	Confirm cladding complete		479	481	1		3.85	501	18	18.04	15.86		480	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('15.86', '501', 4, 1, 479, 481, 480, 12, 'Confirm cladding complete');
56	12	3	4	Check cladding		480	482	1		3.9	501	18	18.04	15.87		481	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('15.87', '501', 4, 1, 480, 482, 481, 12, 'Check cladding');
57	12	3	4	Advise accounts to invoice		481	484	1		3.95	501	18	18.04	15.88		482	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('15.88', '501', 4, 1, 481, 484, 482, 12, 'Advise accounts to invoice');
4	12	1	4	Plumbing		469	null	1		19	500			16		483	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('16.00', '500', 4, 1, 469, null, 483, 12, 'Plumbing');
58	12	4	4	Establish stormwater connection point		483	485	1		4.1	501	19	19.04	16.89		484	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('16.89', '501', 4, 1, 483, 485, 484, 12, 'Establish stormwater connection point');
59	12	4	4	Select plumber		484	486	1		4.2	501	19	19.04	16.9		485	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('16.90', '501', 4, 1, 484, 486, 485, 12, 'Select plumber');
60	12	4	4	Book trencher		485	487	1		4.3	501	19	19.04	16.91		486	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('16.91', '501', 4, 1, 485, 487, 486, 12, 'Book trencher');
61	12	4	4	Issue Purchase order for plumber		486	488	1		4.4	501	19	19.04	16.92		487	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('16.92', '501', 4, 1, 486, 488, 487, 12, 'Issue Purchase order for plumber');
62	12	4	4	Confirm trenching day set	Date:	487	489	1		4.5	501	19	19.05	16.93		488	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('16.93', '501', 4, 1, 487, 489, 488, 12, 'Confirm trenching day set');
63	12	4	4	Confirm plumber booked to start	Date:	488	490	1		4.6	501	19	19.05	16.94		489	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('16.94', '501', 4, 1, 488, 490, 489, 12, 'Confirm plumber booked to start');
64	12	4	4	Confirm trenching done		489	491	1		4.65	501	19	19.05	16.95		490	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('16.95', '501', 4, 1, 489, 491, 490, 12, 'Confirm trenching done');
65	12	4	4	Confirm plumber start	Date:	490	492	1		4.7	501	19	19.05	16.96		491	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('16.96', '501', 4, 1, 490, 492, 491, 12, 'Confirm plumber start');
66	12	4	4	Confirm stormwater installed		491	493	1		4.75	501	19	19.05	16.97		492	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('16.97', '501', 4, 1, 491, 493, 492, 12, 'Confirm stormwater installed');
67	12	4	4	Book final inspection by building surveyor		492	494	1		4.8	501	19	19.05	16.98		493	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('16.98', '501', 4, 1, 492, 494, 493, 12, 'Book final inspection by building surveyor');
68	12	4	4	Confirm final certificate is issued		493	495	1		4.85	501	19	19.05	16.99		494	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('16.99', '501', 4, 1, 493, 495, 494, 12, 'Confirm final certificate is issued');
69	12	4	4	Advise accounts to invoice		494	null	1		4.9	501	19	19.05	17		495	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('17.00', '501', 4, 1, 494, null, 495, 12, 'Advise accounts to invoice');

## Permits
id	user_id	role_id	product_id	display_text	free_text	antecedent_array	decendant_array	reminder_id	change_log	sort_order	tier	xx	x	newSort	SQL	ID
id	owned_by			display_text	free_text	antecedent_array	decendant_array		change_log	sort_order	tier	SQL	SQL2	newSort	SQL	ID
9	13	1	4	Initial Enquiry		null	509	1		5	500			1	INSERT INTO public.job_templates(id, product_id, display_text, antecedent_array, decendant_array, sort_order, tier) VALUES (500, 3, 'Initial Enquiry', ?, ?, ?);	500	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('01.00', '500', 5, 1, null, 509, 500, 13, 'Initial Enquiry');
70	13	13	4	Quote sent date		500	502	1		1	501	5	5.01	1.01		501	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('01.01', '501', 5, 1, 500, 502, 501, 13, 'Quote sent date');
71	13	9	4	3 day follow up – received quote check		500	503	1		2	501	5	5.02	1.02		502	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('01.02', '501', 5, 1, 500, 503, 502, 13, '3 day follow up – received quote check');
72	13	9	4	Site visit requested		500	504	1		3	501	5	5.03	1.03		503	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('01.03', '501', 5, 1, 500, 504, 503, 13, 'Site visit requested');
73	13	9	4	14 days later follow up		500	505	1		4	501	5	5.04	1.04		504	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('01.04', '501', 5, 1, 500, 505, 504, 13, '14 days later follow up');
74	13	9	4	21 days later follow up		500	506	1		5	501	5	5.05	1.05		505	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('01.05', '501', 5, 1, 500, 506, 505, 13, '21 days later follow up');
75	13	9	4	Monthly thereafter follow up (1)		500	507	1		6	501	5	5.06	1.06		506	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('01.06', '501', 5, 1, 500, 507, 506, 13, 'Monthly thereafter follow up (1)');
76	13	9	4	Monthly thereafter follow up (2)		500	508	1		6	501	5	5.06	1.07		507	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('01.07', '501', 5, 1, 500, 508, 507, 13, 'Monthly thereafter follow up (2)');
77	13	9	4	Final Monthly follow up		500	510	1		6	501	5	5.06	1.08		508	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('01.08', '501', 5, 1, 500, 510, 508, 13, 'Final Monthly follow up');
12	13	1	4	Deposit		500	514	1		8	500			4		509	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('04.00', '500', 5, 1, 500, 514, 509, 13, 'Deposit');
82	13	12	4	Deposit date		509	511	1		10	501	8	8.10	4.13		510	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('04.13', '501', 5, 1, 509, 511, 510, 13, 'Deposit date');
83	13	12	4	Distribute information		509	512	1		20	501	8	8.20	4.14		511	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('04.14', '501', 5, 1, 509, 512, 511, 13, 'Distribute information');
84	13	12	4	Building permit admin		509	513	1		30	501	8	8.30	4.15		512	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('04.15', '501', 5, 1, 509, 513, 512, 13, 'Building permit admin');
85	13	12	4	Builder	Date:	509	515	1		40	501	8	8.40	4.16		513	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('04.16', '501', 5, 1, 509, 515, 513, 13, 'Builder');
14	13	1	4	Pre-Permit		509	521	1		10	500			5		514	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('05.00', '500', 5, 1, 509, 521, 514, 13, 'Pre-Permit');
86	13	14	4	Customer quote review / provided		514	516	1		10	501	10	10.10	5.17		515	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('05.17', '501', 5, 1, 514, 516, 515, 13, 'Customer quote review / provided');
87	13	14	4	Customer quote sent		514	517	1		20	501	10	10.20	5.18		516	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('05.18', '501', 5, 1, 514, 517, 516, 13, 'Customer quote sent');
88	13	14	4	Customer acceptance prepped		514	518	1		30	501	10	10.30	5.19		517	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('05.19', '501', 5, 1, 514, 518, 517, 13, 'Customer acceptance prepped');
89	13	14	4	Customer signed acceptance	Date:	514	519	1		40	501	10	10.40	5.2		518	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('05.20', '501', 5, 1, 514, 519, 518, 13, 'Customer signed acceptance');
90	13	14	4	Customer invoiced PP and BP dep	Date:	514	520	1		50	501	10	10.50	5.21		519	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('05.21', '501', 5, 1, 514, 520, 519, 13, 'Customer invoiced PP and BP dep');
91	13	14	4	Payment received	Date:	514	522	1		60	501	10	10.60	5.22		520	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('05.22', '501', 5, 1, 514, 522, 520, 13, 'Payment received');
20	13	1	4	Document Preparation		514	535	1		10.5	500			6		521	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('06.00', '500', 5, 1, 514, 535, 521, 13, 'Document Preparation');
118	13	20	4	Title / POS		521	523	1		12	501	10.5	10.5.12	6.23		522	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('06.23', '501', 5, 1, 521, 523, 522, 13, 'Title / POS');
119	13	20	4	Covenants		521	524	1		13	501	10.5	10.5.13	6.24		523	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('06.24', '501', 5, 1, 521, 524, 523, 13, 'Covenants');
120	13	20	4	BAL rating / BMO		521	525	1		14	501	10.5	10.5.14	6.25		524	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('06.25', '501', 5, 1, 521, 525, 524, 13, 'BAL rating / BMO');
121	13	20	4	Planning permit if required		521	526	1		15	501	10.5	10.5.15	6.26		525	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('06.26', '501', 5, 1, 521, 526, 525, 13, 'Planning permit if required');
122	13	20	4	Proposed site plan		521	527	1		16	501	10.5	10.5.16	6.27		526	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('06.27', '501', 5, 1, 521, 527, 526, 13, 'Proposed site plan');
123	13	20	4	Sewer plan		521	528	1		17	501	10.5	10.5.17	6.28		527	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('06.28', '501', 5, 1, 521, 528, 527, 13, 'Sewer plan');
124	13	20	4	LPOD		521	529	1		18	501	10.5	10.5.18	6.29		528	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('06.29', '501', 5, 1, 521, 529, 528, 13, 'LPOD');
125	13	20	4	RBP selected		521	530	1		19	501	10.5	10.5.19	6.3		529	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('06.30', '501', 5, 1, 521, 530, 529, 13, 'RBP selected');
126	13	20	4	Kit quote		521	531	1		110	501	10.5	10.5.110	6.31		530	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('06.31', '501', 5, 1, 521, 531, 530, 13, 'Kit quote');
127	13	20	4	Construction quote		521	532	1		111	501	10.5	10.5.111	6.32		531	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('06.32', '501', 5, 1, 521, 532, 531, 13, 'Construction quote');
128	13	20	4	Draft Site plan sent to design		521	533	1		112	501	10.5	10.5.112	6.33		532	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('06.33', '501', 5, 1, 521, 533, 532, 13, 'Draft Site plan sent to design');
129	13	20	4	Site plan returned from design		521	534	1		113	501	10.5	10.5.113	6.33999999999999		533	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('06.34', '501', 5, 1, 521, 534, 533, 13, 'Site plan returned from design');
130	13	20	4	Engineering		521	536	1		114	501	10.5	10.5.114	6.34999999999999		534	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('06.35', '501', 5, 1, 521, 536, 534, 13, 'Engineering');
15	13	1	4	Planning Permit		521	542	1		11	500			7		535	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('07.00', '500', 5, 1, 521, 542, 535, 13, 'Planning Permit');
92	13	15	4	Design Site plan		535	537	1		1	501	11	11.01	7.35999999999999		536	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('07.36', '501', 5, 1, 535, 537, 536, 13, 'Design Site plan');
93	13	15	4	Planning permit application submitted	Date:	535	538	1		1	501	11	11.01	7.36999999999999		537	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('07.37', '501', 5, 1, 535, 538, 537, 13, 'Planning permit application submitted');
94	13	15	4	Planning permit fee paid	Date:	535	539	1		2	501	11	11.02	7.37999999999999		538	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('07.38', '501', 5, 1, 535, 539, 538, 13, 'Planning permit fee paid');
95	13	15	4	Planning permit contact	Name:	535	540	1		3	501	11	11.03	7.38999999999999		539	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('07.39', '501', 5, 1, 535, 540, 539, 13, 'Planning permit contact');
96	13	15	4	Follow up schedule		535	541	1		7	501	11	11.07	7.39999999999999		540	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('07.40', '501', 5, 1, 535, 541, 540, 13, 'Follow up schedule');
97	13	15	4	Planning permit issued	Date:	535	543	1		9	501	11	11.09	7.40999999999999		541	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('07.41', '501', 5, 1, 535, 543, 541, 13, 'Planning permit issued');
16	13	1	4	Building Permit		535	null	1		12	500			8		542	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('08.00', '500', 5, 1, 535, null, 542, 13, 'Building Permit');
98	13	16	4	Design Site plan		542	544	1		1	501	12	12.01	8.41999999999999		543	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('08.42', '501', 5, 1, 542, 544, 543, 13, 'Design Site plan');
99	13	16	4	Signed Building Surveyor appointed		542	545	1		2	501	12	12.02	8.42999999999999		544	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('08.43', '501', 5, 1, 542, 545, 544, 13, 'Signed Building Surveyor appointed');
100	13	16	4	Building Permit application submitted date		542	546	1		3	501	12	12.03	8.43999999999999		545	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('08.44', '501', 5, 1, 542, 546, 545, 13, 'Building Permit application submitted date');
101	13	16	4	RFI received		542	547	1		4	501	12	12.04	8.44999999999999		546	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('08.45', '501', 5, 1, 542, 547, 546, 13, 'RFI received');
105	13	16	4	RFI responded		542	548	1		6	501	12	12.06	8.45999999999999		547	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('08.46', '501', 5, 1, 542, 548, 547, 13, 'RFI responded');
106	13	16	4	Building Surveyor Invoice received		542	549	1		7	501	12	12.07	8.46999999999999		548	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('08.47', '501', 5, 1, 542, 549, 548, 13, 'Building Surveyor Invoice received');
107	13	16	4	Balance of BP to be invoiced or not required	2 tick options not yet included: Yes or No	542	550	1		8	501	12	12.08	8.47999999999999		549	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('08.48', '501', 5, 1, 542, 550, 549, 13, 'Balance of BP to be invoiced or not required');
108	13	16	4	Building Surveyor Invoice paid	Date:	542	551	1		9	501	12	12.09	8.48999999999999		550	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('08.49', '501', 5, 1, 542, 551, 550, 13, 'Building Surveyor Invoice paid');
109	13	16	4	Permit issued date	Date:	542	552	1		10	501	12	12.10	8.49999999999999		551	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('08.50', '501', 5, 1, 542, 552, 551, 13, 'Permit issued date');
110	13	16	4	Permit Number	Enter permit number:	542	553	1		11	501	12	12.11	8.50999999999999		552	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('08.51', '501', 5, 1, 542, 553, 552, 13, 'Permit Number');
102	13	16	4	RFI action required 1		542	554	1		05a	501	12	12.05a	8.51999999999999		553	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('08.52', '501', 5, 1, 542, 554, 553, 13, 'RFI action required 1');
103	13	16	4	RFI action required 2		542	555	1		05b	501	12	12.05b	8.52999999999999		554	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('08.53', '501', 5, 1, 542, 555, 554, 13, 'RFI action required 2');
104	13	16	4	RFI action required 3		542	null	1		05c	501	12	12.05c	8.53999999999999		555	INSERT INTO public.job_templates(sort_order, tier, product_id, reminder_id, antecedent_array, decendant_array, id, user_id, display_text) VALUES ('08.54', '501', 5, 1, 542, null, 555, 13, 'RFI action required 3');